**Example of HC-MPC Coordination schedule for Option Period 2**

Copied and edited from Bi-Annual Project Management Plan (OP3-3b; June 7, 2024)

|  |  |  |
| --- | --- | --- |
| **HC-MPC Coordination Dates** | | **OP2 Scheduled Date** |
| 1 | Receive preliminary MPC sample estimate from MEPS-HC Contractor | 12/2/2022 |
| 2 | Receive sample file specifications from MEPS-HC Contractor | 12/9/2022 |
| 3 | Receive 2022 NPI Directory from MEPS-HC Contractor | 1/6/2023 |
| 4 | Receive Prescribed Medication MDDB from AHRQ | 1/6/2023 |
| 5 | Receive Wave 1 Pharmacy Sample Files from MEPS-HC Contractor | 1/12/2023 |
| 6 | AHRQ receives Wave 1 MPC Sample Files from MEPS-HC Contractor | 1/12/2023 |
| 7 | Receive Wave 1 NPIPRVID Files from MEPS-HC Contractor | 1/12/2023 |
| 8 | Receive Non-Pharmacy Sample files from AHRQ | 1/13/2023 |
| 9 | Receive Condition Coding Manual | 3/24/2023 |
| 10 | Receive Wave 2 Pharmacy Sample Files from MEPS-HC Contractor | 4/7/2023 |
| 11 | AHRQ receives Wave 1 MPC Sample Files from MEPS-HC Contractor | 4/7/2023 |
| 12 | Receive Wave 2 NPIPRVID Files from MEPS-HC Contractor | 4/7/2023 |
| 13 | Receive Wave 2 Non-Pharmacy Sample files from AHRQ | 4/12/2023 |
| 14 | Receive from AHRQ Sources of Payment Coding Manual for 2022 coding | 5/12/2023 |
| 15 | MEPS-HC Contractor communicates approximate size of Wave 3 | 5/19/2023 |
| 16 | Receive Wave 3 Pharmacy Sample Files from MEPS-HC Contractor | 7/14/2023 |
| 17 | AHRQ receives Wave 3 MPC Sample Files from MEPS-HC Contractor | 7/14/2023 |
| 18 | Receive Wave 3 NPIPRVID Files from MEPS-HC Contractor | 7/14/2023 |
| 19 | Receive Wave 3 Non-Pharmacy Sample files from AHRQ | 7/17/2023 |
| 20 | Receive GPI coding manual from MEPS-HC Contractor | 8/4/2023 |
| 21 | Receive PROV segments from MEPS-HC Contractor | 8/10/2023 |
| 22 | Receive Condition History table(s) for 2022 from MEPS-HC Contractor | 9/1/2023 |
| 23 | Receive the SOP History Table from MEPS-HC Contractor | 10/5/2023 |
| 24 | Submit to MEPS-HC Contractor VA facilities identified file | 10/13/2023 |
| 25 | Receive MPC "pre-matching " HC file from MEPS-HC Contractor | 10/20/2023 |
| 26 | Receive Weights file from MEPS-HC Contractor | 10/27/2023 |
| 27 | Receive the SOP History Table updated by AHRQ’s review | 11/2/2023 |
| 28 | Submit to MEPS-HC Contractor HHA raw data test files | 12/8/2023 |
| 29 | Submit to MEPS-HC Contractor HHA linked IDs from HHA matching | 12/8/2023 |
| 30 | Receive from MEPS-HC Contractor comments on HHH, NHH, FRMEVPV, and PERSDUPS | 12/22/2023 |
| 31 | Submit to MEPS-HC Contractor MPC raw data test files | 12/22/2023 |
| 32 | Submit to MEPS-HC Contractor linked IDs from MPC test files | 12/22/2023 |
| 33 | Submit to MEPS-HC Contractor HHA raw data production files | 1/12/2024 |
| 34 | Submit to MEPS-HC Contractor linked IDs from HHA production files | 1/12/2024 |
| 35 | Receive from MEPS-HC Contractor comments on test files (OBDF1, HSPF1, OBDF1\_ALL, HSPF1\_ALL) | 1/12/2024 |
| 36 | Receive from MEPS-HC Contractor comments on test files (LINKFIL2, MPSF3P, MATCHES, AUTODUMP\_MEDICAL, MEDICAL\_MATCH) | 1/12/2024 |
| 37 | Submit to MEPS-HC Contractor matched and rolled up data test files for SBD and disavowal file | 1/12/2024 |
| 38 | Submit to MEPS-HC Contractor MPC raw data production files | 1/24/2024 |
| 39 | Submit to MEPS-HC Contractor linked IDs from MPC production files | 1/24/2024 |
| 40 | Receive comments on SBD\_SUM2, NESTED, SBDENCTR test files | 1/26/2024 |
| 41 | Submit to MEPS-HC Contractor MPC matched and rolled up production data file for SBD and disavowal file | 2/15/2024 |
| 42 | Submit to MEPS-HC Contractor Condition History table after MPC coding | 2/16/2024 |
| 43 | Submit to MEPS-HC Contractor SOP History Table after SOP coding | 3/29/2024 |